## project
Project Planner
[6 empty] | Period Highlight: |  |  |  |  | 5 |  |  |  | Plan | Actual | % Complete | Actual (beyond plan) | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | Weeks
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Planning | 1 | 1 | 1 | 1 | 100%
Design/Hardware | 2 | 7 | 2 | 7 | 40%
1st Quadrant | 3 | 2 | 3 | 2 | 40%
1st Revisions | 5 | 1 | 5 | 1 | 0%
2nd Quadrant | 4 | 2 | 4 | 2 | 40%
2nd Revisions | 6 | 1 | 6 | 1 | 0%
3rd Quadrant | 5 | 2 | 5 | 2 | 0%
3rd Revisions | 7 | 1 | 7 | 1 | 0%
4th Quadrant | 6 | 2 | 6 | 2 | 40%
4th Revisions | 8 | 1 | 8 | 1 | 0%
Review | 9 | 1 | 9 | 1 | 0%
Report Writing | 1 | 9 | 1 | 9 | 50%